## Innovations
ID | Title | Observation | Category | KPIAffected | Context | LessonLearned | Recommendation | ExpectedBenefit | Comment | Project | ImprovementDate | ValueIn$ | ContactName | ContactPhone | ContactEmail | BusinessArea | Impact | ImpactGroup | ImprovementType | ImplementationEase | InnovationType
1 | Issue Resolution Process | * Clarity around the process for both users and the various technology resources could be improved. This has impacted to resolve the issue, the effectiveness of the outcome and in general resulted in confusion. * Communication from the various stakeholders when working on technical issues is not formalised and results in those involved not knowing the most recent status of the issue. This communication breakdown extended to the users. | Communication | On time delivery | Introduction of a new client to the National Self Insurance business. Use existing client technology and transfer the data and meta-data to a new system. | Better issue resolution processes are required to improve speed of implementation. | * Formalise, document and communicate issue resolution process with all self insurance employees * Clarify, formalise roles and responsibilities and process for technology resources * Consider centralised system for issue tracking | Improved communication Reduced confusion Reduced duplication with role cross-over Improved visibility for project oversight | Issue Resolution Process | Technology Introduction | 2014-02-01 |  | Frances Calamari | 02 8251 9190 | F.Calamari@fishtank.com | Sales Management | Business Unit | Team | Technology | Moderate | Lesson Learned
2 | Communication and Visibility of Plans and Decisions | Limited visibility of the overall plans, move dates etc. have resulted in uncertainty with when technology elements are required to be delivered. This has resulted in jobs being completed quickly with limited time for testing thoroughly. | Integration | On time delivery | Introduction of a new client to the National Self Insurance business. Use existing client technology and transfer the data and meta-data to a new system. | * Implement weekly Steering Committee meeting * Develop formal plans and implement governance controls * Implement weekly working group meeting working from project plan with clearly defined roles and tasks | * Implement weekly Steering Committee meeting * Develop formal plans and implement governance controls * Implement weekly working group meeting working from project plan with clearly defined roles and tasks | Improved communication Reduced confusion Reduced duplication with role cross-over | Communication and Visibility of Plans and Decisions | Technology Introduction | 2014-02-01 |  | Rachael Bream | 02 8098 6323 | r.bream@fishtank.com | Claims Management | Business Unit | Team | Technology | Moderate | Lesson Learned
3 | Testing Process | Have not covered all elements of technology and therefore gaps have resulted in issues including access to systems, printing etc. | Quality | On time delivery | Introduction of a new client to the National Self Insurance business. Use existing client technology and transfer the data and meta-data to a new system. | * Establish formal testing process including both operational and technical elements * Include testing in the project plan and ensure allocated resources, and sufficient time allocated * Implement testing hub based in Sydney office for ease of issues resolution | * Establish formal testing process including both operational and technical elements * Include testing in the project plan and ensure allocated resources, and sufficient time allocated * Implement testing hub based in Sydney office for ease of issues resolution | Process improvement | Testing Process | Technology Introduction | 2014-02-01 |  | Richard Hemsworth | 02 8860 8601 | richard@sandar.com.au | Sales Management | Business Unit | Team | Technology | Moderate | Lesson Learned
4 | Project Roles and Responsibilities | Conflicting direction regarding approach on execution of tasks. This is has resulted in various project resources unsure of who is responsible for making final decisions | Quality | On time delivery | Introduction of a new client to the National Self Insurance business. Use existing client technology and transfer the data and meta-data to a new system. | * Clearly define roles as part of the Steering Committee and working group meetings | * Clearly define roles as part of the Steering Committee and working group meetings | Improved governance Reduced time spent on multiple oversight functions | Project Roles and Responsibilities | Technology Introduction | 2014-02-01 |  | Frank Snapper | 02 8251 9190 | F.Snapper@fishtank.com | Facilities | Business Unit | Team | Technology | Moderate | Lesson Learned